DELIVERY ROADMAP

Credit Card Fraud Detection — 29 July to 12 August 2026

Delivery objective. Deliver a working, tested, orchestrated fraud-data pipeline with clear documentation and a team-ready demo by 12 August.

# Priority Order

Core pipeline first: S3 → Databricks Bronze → Databricks Silver → Snowflake Raw → Snowflake Analytics.

Mandatory Databricks Workflows orchestration and end-to-end validation second.

Documentation, architecture, test evidence, PPT, and rehearsal third.

Bonus natural-language query website only after all core items are stable.

# Workstream Roadmap

| Workstream | Target dates | Definition of done |
| --- | --- | --- |
| Foundation and ingestion | 29 Jul–1 Aug | Repository, roles, access, S3 folders, source profiling, and a successful Bronze load. |
| Transformation | 2–4 Aug | Silver cleaning, auditability, feature engineering, rejects handling, and validations. |
| Warehouse and analytics | 5–7 Aug | Snowflake Raw load, analytics tables, High-Risk Queue, and reconciliation. |
| Orchestration | 7–8 Aug | Databricks Workflow runs all required tasks in sequence with logs, retries, and alerts. |
| Evidence and delivery | 8–11 Aug | Tests, README, data model, architecture, AI usage, PPT, and completed rehearsal. |
| Submission and review | 12 Aug | Final successful run, evidence captured, artifacts submitted, team ready to present. |

# Critical Milestones

| Milestone | Due | Go / no-go check |
| --- | --- | --- |
| M1: Bronze works | 1 Aug | S3 source row count matches bronze.transactions_raw. |
| M2: Silver works | 4 Aug | Features and quality checks are complete; invalid records handled. |
| M3: Analytics works | 7 Aug | Snowflake tables, High-Risk Queue, and validation views are queryable. |
| M4: Workflow works | 8 Aug | Databricks Workflow completes end-to-end successfully. |
| M5: Review ready | 11 Aug | All artifacts complete and every member has rehearsed their section. |
| M6: Submission | 12 Aug | Final evidence and deliverables submitted. |

# Risk Controls

Do not start bonus work until M4 is complete.

Use daily 15-minute stand-ups to remove access or integration blockers.

Commit working changes to Git every day.

Capture screenshots, query results, and test logs as evidence as soon as each stage works.

Keep a simple fallback demo: run the pipeline on a known input file and show persisted results.